## project-gantt
Project Gantt for SAMS
Introduction
Name | Task owner | Status | Task Timeline - Start | Task Timeline - End | Priority | Dependent on
Purpose | Sainath | Done | 2020-10-24 | 2020-10-25 | Critical | All Stakeholders and Client/Developers
Document Conventions | Sainath ,Ravi , Shaik Hussain , Rakesh | Done | 2020-11-27 | 2020-11-28 | Low
Intended Audience and Reading Suggestions | Ravi , Shaik Hussain , Rakesh | Done | 2020-10-28 | 2020-10-30 | Low
Problem Description | Sainath | Done | 2020-10-24 | 2020-10-25 | High
Product Scope and References | Sainath | Done | 2020-10-24 | 2020-10-25 | Medium
Overall Description
Name | Task owner | Status | Task Timeline - Start | Task Timeline - End | Priority | Dependent on
Software Architecture | Sainath , Mahendar | Done | 2020-11-01 | 2020-11-02 | Critical | All Team
Product Functions and Use Cases | Sainath , Ravi , Shaik Hussain, Rakesh | Done | 2020-11-03 | 2020-11-04 | High
User and Stakeholders | Sainath , Mahendar | Done | 2020-11-03 | 2020-11-04 | Medium
Operating Environment | Sainath , Mahendar | Done | 2020-11-06 | 2020-11-06 | High
User Documentation | Sainath , Mahendar | Done | 2020-11-05 | 2020-11-06 | Medium
Assumptions and Dependencies | Sainath | Done | 2020-11-05 | 2020-11-06 | Medium
Design and Implementation Constraints | Sainath , Mahendar | Done | 2020-11-11 | 2020-11-24 | Critical
External Interface Requirements
Name | Task owner | Status | Task Timeline - Start | Task Timeline - End | Priority | Dependent on
User Interfaces | Sainath Reddy, Mahendar, Ravi | Done | 2020-11-24 | 2020-11-24 | Medium | Operating Environment
Hardware Interfaces | Sainath Reddy , Rakesh | Done | 2020-11-25 | 2020-11-25 | Medium | User Interfaces
Software Interfaces | Sainath, Mahendar | Done | 2020-11-26 | 2020-11-26 | Medium | Hardware Interfaces
Communications Interfaces | All team | Done | 2020-11-27 | 2020-11-27 | Medium | Software Interfaces
System Requirements
Name | Task owner | Status | Task Timeline - Start | Task Timeline - End | Priority | Dependent on
Requirement F1 | Sainath Reddy, Mahendar, | Done | 2020-11-07 | 2020-11-08 | High | End Users/Stakeholders
Requirement F2 | Sainath Reddy, Mahendar | Done | 2020-11-09 | 2020-11-11 | High | End Users/Stakeholders
User Stories and Scenarios
Name | Task owner | Status | Task Timeline - Start | Task Timeline - End | Priority | Dependent on
User stories and their requirements | Sainath Reddy, Ravi , Shaik Hussain | Done | 2020-11-08 | 2020-11-09 |  | End Users
Other Nonfunctional Requirements
Name | Task owner | Status | Task Timeline - Start | Task Timeline - End | Priority | Dependent on
Performance Requirements | All team | Done | 2020-11-29 | 2020-11-29 |  | Design/FR/NFR
Safety Requirements | All team | Done | 2020-11-29 | 2020-11-29 |  | Design/FR/NFR
Security Requirements | All team | Done | 2020-11-29 | 2020-11-29 |  | Design/FR/NFR
Software Quality Attributes | All team | Done | 2020-11-29 | 2020-11-29 |  | Design/FR/NFR
Other External Requirements | All team | Done | 2020-11-29 | 2020-11-29 |  | Design/FR/NFR
Business Rules | Sainath Reddy , Mahendar | Done | 2020-11-29 | 2020-11-29 |  | FR
Test Plan
Name | Task owner | Status | Task Timeline - Start | Task Timeline - End | Priority | Dependent on
System Testing | All team | Done | 2020-11-29 | 2020-11-29 | Critical | Design and Implementation Constraints
Load Testing | All team | Done | 2020-11-29 | 2020-11-29 | High
Performance Tsting | All team | Done | 2020-11-29 | 2020-11-29 | High
Unit Test | Sainath Reddy , Mahendar | Done | 2020-12-09 | 2020-12-09 | Medium
Project Management
Name | Task owner | Status | Task Timeline - Start | Task Timeline - End | Priority | Dependent on
Task Assignment | Sainath Reddy | Done | All the time , as a project leader all the tasks assigned to team should be monitored and tracked and managed |  | Critical | Project Leader
Monitoring | Sainath Reddy | Done |  |  | High | Project Leader
Collaboration | Sainath Reddy | Done |  |  | Critical | Project Leader
Periodic Calls | Sainath Reddy | Done |  |  | High | Project Leader
Knowledge Sharing | Sainath Reddy | Done |  |  | High | Project Leader
Trello Board updates/SRS Documentation | Sainath Reddy | Done |  |  | Critical | Project Leader

## project-gantt-updates
Project Gantt | Updates
Item ID | Item Name | Content Type | Content Type | User | Created At | Update Content | Likes Count | Asset IDs | Post ID | Parent Post ID
881678726 | Document Conventions | Update |  | Sainath Reddy | 03/December/2020 11:51:20 AM | Completed | 0 |  | 853175576